## Sheet1
Semester project
Tasks | Start date |  | Completion | Adjusted length | Person | Role
Planning 1 | 2024-09-22 |  | 2024-09-24 | 2 | Jakub Dubrava | Manager/Schedule
Simulation 1 | 2024-09-24 |  | 2024-09-27 | 3 | Katharina Johannsen | Designer
Design 1 | 2024-09-27 |  | 2024-10-04 | 7 | Milan Caban | Programmer/Embbeded expert
Software 1 | 2024-10-04 |  | 2024-10-10 | 6 | Roko Grgic | Practical electronics
Hardware 1 | 2024-10-04 |  | 2024-10-10 | 6
Planning 2 | 2024-10-13 |  | 2024-10-15 | 2 | Meeting roles | Week 39 + 40 | Week 41+42 | Week 43+44 | Week 45+46
Simulation 2 | 2024-10-15 |  | 2024-10-18 | 3 | Guide | Jakub | Millan | Kati | Roko
Design 2 | 2024-10-18 |  | 2024-10-25 | 7 | Reporter | Kati | Roko | Jakub | Milan
Software 2 | 2024-10-23 |  | 2024-10-31 | 8
Hardware 2 | 2024-10-23 |  | 2024-10-31 | 8
Buffer zone | 2024-11-03 |  | 2024-11-26 | 23
Report writing | 2024-09-23 |  | 2024-11-26 | 64